## Target tracking
Target Tracking
Subsystem | Target | Progress | Due date | Key
Job decider | Read file and return info |  | 2018-03-12 |  | = not started
Route planner | basic algorithm in place |  | 2018-03-12 |  | = currently being worked on
Job assignment | Evenly assign jobs |  | 2018-03-12 |  | = completed
Networking | Single bluetooth connection for one robot |  | 2018-03-12
GUI | Simplified PC GUI |  | 2018-03-12
Robot movement | Split grid movement into methods |  | 2018-03-12
All | Fully integrate |  | 2018-03-18
All | Begin whole system testing |  | 2018-03-18
All | Complete project |  | 2018-03-20